## 11-11-2019
EE200D CAPSTONE PROJECT
MINUTES OF THE MEETING
NOV. 11, 2019, MITL CONFERENCE ROOM
Date | Matters Discussed | Type D-elivrable, I-nformation | Responsible | Estimated Completion Date | Actual Completion Date | Status | Remarks
2019-11-11 | Minutes of Meeting Format | I | Sir Manalo | 2019-11-11 | 2019-11-11 | Completed |  | I | Marcaida | Completed
| Schedule of Activities | D | Marcaida & Muniz |  | 2019-12-31 | Pending | Moving target. Fine-tuning on-going until activities are clear. | D | Muñiz | Pending
| Acquire hardware (Arduino UNO, Atmega 328p, etc.) | D | Marcaida | 2019-11-21 |  | Pending |  |  | Sir Manalo | Rescheduled
| Conduct Mechanical Loss Experiment and determine dc motor armature resistance | D | Muñiz | 2019-11-22 |  | Pending |  |  | Marcaida & Muniz | Cancelled
All